## Sheet1
Story ID | User Story | Sprint | Type | Priority | Status | Points | Members
1 | As a player, I want to be able to select different levels to attempt. |  | F | M | W | 7
2 | As a player, I want to be able to adjust the game volume. |  | F | L | W | 2
3 | As a player, I want to control a character which can be moved to the left and right. |  | F | H | W | 9
4 | As a player, I want my character to be able to jump. |  | F | H | W | 7
5 | As a player, I want my character to be able to fire bullets. |  | F | M | W | 9
6 | As a player, I want to encounter enemy characters that can be overcome through battle or circumvention. |  | F | M | W | 7
7 | As a player, I want to be able to collect some goal item at the end of each level. |  | F | H | W | 3
8 | As a player, I want to be able to change the background music, and I want the music to change the functionality of my character. |  | F | H | W | 8
9 | As a player, I want to be able to collect bonus items within different levels, which will unlock new music tracks. |  | F | L | W | 4
10 | As a player, I want an end-of-level screen to be display my completion time before I return to the menu. |  | F | H | W | 4
11 | As a player, I want to be able to view my best times for each level. |  | F | L | W | 5
12 | As a player, I want to be able to share my best times with my friends via social media. |  | F | L | W | ???
13 | As a player, I want to be able to view the game's credits (said no one ever.) |  | F | H | W | 2
14 | As a player, I want to be able to play a tutorial level that will guide me through the game's controls. |  | F | M | W | 9
15 | As a player, I want to be able to toggle the sound effects off in the game. |  | F | L | W | 3
16 | As a player, I want to be able to unlock new levels by completing existing levels. |  | F | L | W | 3
17 | As a player, I want to be able to access a pause menu where I can resume the game, restart the level, or return to the main menu. |  | F | M |  | 5